## Intro
State of North Carolina Community Development Block Grant – Mitigation (CDBG-MIT) Program Projections of Expenditures and Outcomes - as of Quarter 3 Ending September 30, 2024 Grant #P-18-NC-37-MIT1 Background: The Federal Register notice authorizing North Carolina’s allocation of CDBG-MIT funds requires the State to publish a projection of expenditures and outcomes. The following projections follow a HUD-specified template designed to distinguish investments in housing, non-housing and planning/administrative activities. This reflects the grant amount through six years of performance. According to 84 FR 45838 which allocated the funds to the State of North Carolina, the period of performance is through 12 years. One half of the allocated funds must be expended in the first six years of performance. These quarterly projections will be updated as the grant proceeds. Some programs are not scheduled to end service until after the first six years of the grant, although the majority of funds are expected to be expended prior to six years. The original CDBG-MIT Action Plan was approved by HUD on March 13, 2020 and Substantial Action Plan Amendment 1 to the Action Plan (SAPA1) was approved March 9, 2021. This projection of expenditures and outcomes is in consideration of the content of SAPA5. Reading the Projections: The HUD format contains two spreadsheets: one for financial projections and one for performance indicators. The projections indicate a month and year that corresponds to the beginning of the quarter. For example, 01/2020 represents the quarter from 01/01/2020-9/30/2020. The graphs represent cumulative expenditures over the life of the programs. Revisions: These projections will be revised as more data becomes available through the award process. Additionally, these projections will be revised following Quarterly Performance Reports submitted to HUD to reflect actual progress. Beginning with the projections updated for the period ending June 30, 2021, the projection for buyout cost is adjusted to match the current market value (CMV) approach. In this approach, property values are expected to appreciate over time and so the cost of the buyout activity increases 3% annually. The incentive structure likewise increases, as the incentives were restructured to cover replacement housing costs more completely than the previous incentive model. Not all buyout participants will receive an incentive, but the vast majority are expected to receive some kind of incentive structure along with the buyout activity. The incentive is projected to occur after buyout is completing, resulting in a lag of approximately a quarter after the buyout of each property. With the addition of $34.6 million in CDBG-MIT funds allocated to the State in 86 FR 561, the projections have been extended approximately two years in to calendar year 2028. This is within the allowable period of performance.

## Performance Proj
Buyout | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14.5 | 29.5 | 44.5 | 74.5 | 104.5 | 144.5 | 149.5 | 159.5 | 169.5 | 179.5 | 189.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5 | 199.5
# of Units Aquired (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 12 | 15 | 15 | 30 | 30 | 40 | 5 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 40 | 44 | 55 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66
# of Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 26 | 4 | 11 | 11
|  |  |  | 50000 | a year 2021 buyout
|  |  |  | 51500 | 2022
|  |  |  | 53045 | 2023
2024
|  |  |  | 0 | 2025
|  |  |  | 0 | 2026
|  |  |  | 0 | 2027
|  |  |  | 0 | 2028
Housing Incentives | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 14 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 27 | 32 | 32 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
# of Housing Incentives (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Incentives (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PHA Construction of New Housing | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 90 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 158 | 158 | 158
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0
PHA Residential Rehab and Reconstruction | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 41 | 41 | 41 | 41 | 41 | 41 | 41
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Public Facilities | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 7 | 7 | 11 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 19 | 19 | 19 | 19 | 19
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
# of Public Facilities (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 2
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0
Public Infrastructure | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350 | 2350
# of Linear Feet of Public Improvements (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements | 0
Dike/dam/stream-river bank repairs
# of Linear Feet of Public Improvements | 0
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements | 0
Public Services | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Down Payment Assistance Provided | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 17 | 27 | 37 | 57 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
# of Down Payment Assistance Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 10 | 10 | 10 | 20 | 23 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual # Down Payment Assistance Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Down Payment Assistance Payments (From QPR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction of New Housing | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Financial Proj
Buyout | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 0 | 0 | 51196.5 | 1396995.41 | 1828831.36 | 5869022.93 | 6889035.93 | 7903076.08 | 7944165.05 | 11338167.15 | 12222903.41 | 14775198.96 | 15211645.54 | 17252233.6 | 19618576.57 | 21450318.07 | 23456166.2062 | 25462014.3424 | 27467862.4786 | 29473710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148 | 31723710.6148
Quarterly Projection | 0 | 0 | 51196.5 | 1345798.91 | 431835.95 | 4040191.57 | 1020013 | 1014040.15 | 41088.97 | 3394002.1 | 884736.26 | 2552295.55 | 436446.58 | 2040588.06 | 2366342.97 | 1831741.5 | 2005848.1362 | 2005848.1362 | 2005848.1362 | 2005848.1362 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 0 | 51196.5 | 1396995.41 | 1828831.36 | 5869022.93 | 6889035.93 | 7903076.08 | 7944165.05 | 11338167.15 | 12222903.41 | 14775198.96 | 15211645.54 | 17252233.6 | 19618576.57 | 21450318.07 | 23920380.07 | 26332576.27 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76 | 28776994.76
Actual Quarterly Expend (from QPRs) | 0 | 0 | 51196.5 | 1345798.91 | 431835.95 | 4040191.57 | 1020013 | 1014040.15 | 41088.97 | 3394002.1 | 884736.26 | 2552295.55 | 436446.58 | 2040588.06 | 2366342.97 | 1831741.5 | 2470062 | 2412196.2 | 2444418.49 | 0
Housing Incentives | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394737 | 789474 | 1184211 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948 | 1578948
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394737 | 394737 | 394737 | 394737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0
PHA Housing | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1647587.0909 | 3295174.1818 | 4942761.2727 | 6590348.3636 | 8237935.4545 | 9885522.5455 | 11533109.6364 | 13180696.7273 | 14828283.8182 | 16475870.9091 | 18123458 | 19771045.0909 | 21418632.1818 | 23066219.2727 | 24713806.3636 | 26361393.4545 | 28008980.5455 | 29656567.6364 | 31304154.7273 | 32951741.8182 | 34599328.9091 | 36246916
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909 | 1647587.0909
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3256288.85 | 3608365.54 | 3733851.54 | 3889434.37 | 4370007.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14 | 4410895.14
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3256288.85 | 352076.69 | 125486 | 155582.83 | 480572.77 | 40888
Non-Housing | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 1390015 | 1144000 | 1690000 | 1940000 | 2190000 | 2290000 | 2480000 | 4080000 | 4730000 | 5330000 | 5830000 | 7580000 | 10330000 | 13080000 | 15830000 | 18580000 | 21330000 | 24130000 | 26930000 | 29830000 | 31230000 | 32030000 | 32780000 | 33430000 | 34030000 | 34530000 | 34980000 | 35330000 | 35500000
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 1390015 | 0 | 250000 | 250000 | 250000 | 100000 | 190000 | 1600000 | 650000 | 600000 | 500000 | 1750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2800000 | 2800000 | 2900000 | 1400000 | 800000 | 750000 | 650000 | 600000 | 500000 | 450000 | 350000 | 170000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664393.16 | 2664393.16 | 2758718.16 | 3128726.17 | 5438276.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94 | 6589074.94
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664393.16 | 0 | 94325 | 370008.01 | 2309550.77 | 1150798
NCAS Financial Reports | [7 empty] | 7BAM/Buyout & Acquisition | 0
[8 empty] | 7SBA/Economic Development SBA (Transfer to Commerce) | 0
[8 empty] | 7SRM/Small Rental | 0 |  |  |  | 72864.46 | 143328.25 | 73721.93 |  | 3432.45
[8 empty] | 7MFM Multi-Family | 0 |  |  |  |  | 638569.33 | 0 | 1646157.27 | 26012.7
[8 empty] | TOTAL Non-Housing | 0 | 0 | 0 | 0 | 72864.46 | 781897.58 | 73721.93 | 1646157.27 | 29445.15
Housing | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56739.3441
Planning and Admin | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 18913.1147 | 37826.2294 | 161391.9121 | 353044.8076 | 574958.6867 | 993665.9489 | 1469112.5552 | 1967254.8991 | 2525919.2101 | 3331326.925 | 4208604.4758 | 5085882.0266 | 6122997.0266 | 7160110.0266 | 8197223.0266 | 9234336.0266 | 10271449.0266 | 11308562.0266 | 12345675.0266 | 12487011.0266 | 12628347.0266 | 12769683.0266 | 12911019.0266 | 13052355.0266 | 13193691.0266 | 13335027.0266 | 13476363.0266 | 13617699.0266 | 13759035.0266 | 13900371.0266 | 14041707.0266 | 14183043.0266 | 14324379.0266 | 14465715.0266 | 14607051.0266
Quarterly Projection | 18913.1147 | 18913.1147 | 123565.6827 | 191652.8956 | 221913.8791 | 418707.2622 | 475446.6063 | 498142.3439 | 558664.311 | 805407.715 | 877277.5508 | 877277.5508 | 1037115 | 1037113 | 1037113 | 1037113 | 1037113 | 1037113 | 1037113 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336 | 141336
Actual Expenditure | 0 | 0 | 222942.19 | 233141.15 | 240779.15 | 256066.95 | 317236 | 346652.92 | 393251.51 | 1084981.7 | 1134493.7 | 1265968.7 | 1332367.7 | 1551669.25 | 1713080.4 | 1715181.96 | 1805284.96 | 2113983.55 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24 | 3697686.24
Actual Quarterly Expend (from QPRs) | 0 | 0 | 222942.19 | 10198.96 | 7638 | 15287.8 | 61169.05 | 29416.92 | 46598.59 | 691730.19 | 49512 | 131475 | 66399 | 219301.55 | 161411.15 | 2101.56 | 90103 | 308698.59 | 1583702.69 | 0
Total Expenditures | 01/2020 | 04/2020 | 07/2020 | 10/2020 | 01/2021 | 04/2021 | 07/2021 | 10/2021 | 01/2022 | 04/2022 | 07/2022 | 10/2022 | 01/2023 | 04/2023 | 07/2023 | 10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
Projected Expenditures | 18913.1147 | 37826.2294 | 212588.4121 | 1750040.2176 | 2403790.0467 | 6862688.8789 | 9748163.4852 | 11260345.9791 | 12110099.2601 | 16559509.075 | 18571522.8858 | 22101095.9866 | 23764657.5666 | 30089945.7175 | 35790988.7784 | 40907430.3693 | 46492715.5964 | 53328000.8235 | 61163286.0506 | 68102794.2777 | 74891717.3687 | 79430640.4596 | 83969563.5505 | 88558486.6414 | 93147409.7323 | 97836332.8232 | 101025255.9141 | 103614179.005 | 106153102.0959 | 108592025.1868 | 110980948.2777 | 113269871.3687 | 115508794.4596 | 117647717.5505 | 119606640.6414
Quarterly Projection | 18913.1147 | 18913.1147 | 174762.1827 | 1537451.8056 | 653749.8291 | 4458898.8322 | 2885474.6063 | 1512182.4939 | 849753.281 | 4449409.815 | 2012013.8108 | 3529573.1008 | 1663561.58 | 6325288.1509 | 5701043.0609 | 5116441.5909 | 5585285.2271 | 6835285.2271 | 7835285.2271 | 6939508.2271 | 6788923.0909 | 4538923.0909 | 4538923.0909 | 4588923.0909 | 4588923.0909 | 4688923.0909 | 3188923.0909 | 2588923.0909 | 2538923.0909 | 2438923.0909 | 2388923.0909 | 2288923.0909 | 2238923.0909 | 2138923.0909 | 1958923.0909
Actual Expenditure | 0 | 0 | 274138.69 | 1630136.56 | 2069610.51 | 6125089.88 | 7206271.93 | 8249729 | 8337416.56 | 12423148.85 | 13357397.11 | 16041167.66 | 16544013.24 | 18803902.85 | 27252338.98 | 29438258.73 | 32218234.73 | 35464720.36 | 42302965.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08 | 43494651.08
Actual Quarterly Expend (from QPRs) | 0 | 0 | 274138.69 | 1355997.87 | 439473.95 | 4055479.37 | 1081182.05 | 1043457.07 | 87687.56 | 4085732.29 | 934248.26 | 2683770.55 | 502845.58 | 2259889.61 | 8448436.13 | 2185919.75 | 2779976 | 3246485.63 | 6838244.72 | 1193656 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1
Housing with the $44m transfer of HRP projects:
10/2023 | 01/2024 | 04/2024 | 07/2024 | 10/2024 | 01/2025 | 04/2025 | 07/2025 | 10/2025 | 01/2026 | 04/2026 | 07/2026 | 10/2026 | 01/2027 | 04/2027 | 07/2027 | 10/2027 | 01/2028 | 04/2028 | 07/2028
0 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000
0 | 44000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0