## Intro
State of North Carolina Community Development Block Grant – Disaster Recovery (CDBG-DR) Program Projections of Expenditures and Outcomes - as of Quarter Ending March 31, 2022 Grant # B-16-DL-37-0001 Background: The Federal Register notice authorizing North Carolina’s allocation of CDBG-DR funds requires the State to publish a projection of expenditures and outcomes. The following projections follow a HUD-specified template designed to distinguish investments in housing, non-housing and planning/administrative activities. This update reflects the entire grant amount. Reading the Projections: The HUD format contains two spreadsheets: one for financial projections and one for performance indicators. The projections indicate a month and year that corresponds to the beginning of the quarter. For example, 7/2018 represents the quarter from 7/1/2018-9/30/2018. The graphs represent cumulative expenditures over the life of the programs. Revisions: These projections will be revised as more data becomes available through the award process. Additionally, these projections will be revised following Quarterly Performance Reports submitted to HUD to reflect actual progress.

## Financial Proj
[9 empty] | (MtD July) | QtD thru 9/30/19 | QtD thru 12/31/19 | QtD thru 3/31/20 | QtD thru 06/30/20 | QtD thru 9/30/20 | QtD thru 12/31/20 | QtD thru 03/31/21 | QtD thru 06/30/21 | QtD thru 12/31/21 | QtD thru 03/31/22 | QtD thru 06/30/22 | QtD thru 09/30/22
Housing | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 1242225.57 | 3519357.57 | 8925666.57 | 14805059.57 | 25315464.57 | 39636968.57 | 53551420.57 | 71718642.57 | 81511494.1058 | 91304345.6417 | 101097197.1775 | 110890048.7133 | 120682900.2492 | 130475751.785 | 136929820.785 | 143383889.785 | 149837958.785 | 156292027.785 | 162746096.785 | 168200167.785 | 173654238.785 | 179108309.785 | 184562380.785 | 190016451.785 | 195470522.785 | 197470522.785 | 198265440.785 | 199022549.785
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 1242225.57 | 2277132 | 5406309 | 5879393 | 10510405 | 14321504 | 13914452 | 18167222 | 9792851.5358 | 9792851.5358 | 9792851.5358 | 9792851.5358 | 9792851.5358 | 9792851.5358 | 6454069 | 6454069 | 6454069 | 6454069 | 6454069 | 5454071 | 5454071 | 5454071 | 5454071 | 5454071 | 5454071 | 2000000 | 794918 | 757109
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 1242225.57 | 3519357.57 | 8925666.57 | 17309425.59 | 27819830.59 | 39547644.14 | 53452934.1 | 71318020.1 | 84228609.59 | 95435854.4 | 107278751.03 | 113348868.48 | 119960968.84 | 128602880.84 | 133973327 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5 | 152701075.5
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 1242225.57 | 2277132 | 5406309 | 8383759.02 | 10510405 | 11727813.55 | 13905289.96 | 17865086 | 12910589.49 | 11207244.81 | 11842896.63 | 6070117.45 | 6612100.36 | 8641912 | 5370446.16 | 18727748.5
NCAS Financial Reports | [7 empty] | 8911/Housing Rehab (Grant Local Gov't) | 1993806.53 | 3273650.81 | 3273650.81 | 0
[8 empty] | 7HRB Housing (Single Family) |  | 5065858.72 | 14019122.07 | 11111338.52 | 13316653.92 | 17013941.11 | 12895595.62 | 13022351.89 | 9436208.26
[8 empty] | TOTAL Housing | 1993806.53 | 8339509.53 | 17292772.88 | 11111338.52 | 13316653.92 | 17013941.11 | 12895595.62 | 13022351.89 | 9436208.26
Non-Housing | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Expenditures | 0 | 0 | 0 | 277283 | 864283 | 1185000 | 1935000 | 2135000 | 3560000 | 3609985 | 3859985 | 4109985 | 4359985 | 4459985 | 4559985 | 5059985 | 5559985 | 6309985 | 7059985 | 7809985 | 8809985 | 9809985 | 10809985 | 11809985 | 13309985 | 14809985 | 16409985 | 18009985 | 19500000 | 20500000 | 21500000 | 22000000 | 22500000
Quarterly Projection | 0 |  |  | 277283 | 587000 | 320717 | 750000 | 200000 | 1425000 | 49985 | 250000 | 250000 | 250000 | 100000 | 100000 | 500000 | 500000 | 750000 | 750000 | 750000 | 1000000 | 1000000 | 1000000 | 1000000 | 1500000 | 1500000 | 1600000 | 1600000 | 1490015 | 1000000 | 1000000 | 500000 | 500000
Actual Expenditure | 0 | 0 | 0 | 277283 | 864283 | 1185000 | 1935000 | 2135000 | 3560000 | 3609985 | 3609985 | 3609985 | 3609985 | 3653646.9 | 3653646.9 | 3653646.9 | 3653646.9 | 3653646.9 | 4975185.9 | 4975185.9 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84 | 5043223.84
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 277283 | 587000 | 320717 | 750000 | 200000 | 1425000 | 49985 | 0 | 0 | 0 | 43661.9 | 0 | 0 | 0 | 0 | 1321539 | 0 | 68037.94
NCAS Financial Reports | [7 empty] | 7BAM/Buyout & Acquisition | 0 | 17618.31 | 0 | 0 | 9163 | 940705.8 | 96905.05 | 0 | -1019587.37
[8 empty] | 7SBA/Economic Development SBA (Transfer to Commerce) | 0 | 1425000 | 49985 | 0 | 0 | 0 | 43661.9
[8 empty] | 7SRM/Small Rental | 0 |  |  |  | 72864.46 | 143328.25 | 73721.93 |  | 3432.45
[8 empty] | 7MFM Multi-Family | 0 |  |  |  |  | 638569.33 | 0 | 1646157.27 | 26012.7
[8 empty] | TOTAL Non-Housing | 0 | 1442618.31 | 49985 | 0 | 82027.46 | 1722603.38 | 214288.88 | 1646157.27 | -990142.22
Planning & Admin | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Expenditures | 0 | 0 | 0 | 578685.9 | 1695563.76 | 2464354.82 | 3428817.56 | 4083338.56 | 6210201.6 | 8411874.6 | 9585784.6 | 12371382.6 | 13048080.2 | 13548080.2 | 13739672.2 | 13889672.2 | 14039672.2 | 14189672.2 | 14339672.2 | 14419672.2 | 14499672.2 | 14579672.2 | 14659672.2 | 14739672.2 | 14819672.2 | 14899672.2 | 14899672.2 | 14899672.2 | 14899672.2 | 14899672.2 | 14899672.2 | 14899672.2 | 14899672.2
Quarterly Projection | 0 |  |  | 578685.9 | 1116877.86 | 768791.06 | 964462.74 | 654521 | 2126863.04 | 2201673 | 1173910 | 2785598 | 676697.6 | 500000 | 191592 | 150000 | 150000 | 150000 | 150000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 578685.9 | 1695563.76 | 2464354.82 | 3428817.56 | 4083338.56 | 6210201.6 | 8411874.6 | 9585784.6 | 12371382.6 | 13048080.2 | 14163213.99 | 14215479.33 | 14487603.62 | 14820010.92 | 14896224.38 | 15222735.61 | 15222877.07 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53 | 15227664.53
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 578685.9 | 1116877.86 | 768791.06 | 964462.74 | 654521 | 2126863.04 | 2201673 | 1173910 | 2785598 | 676697.6 | 1115133.79 | 52265.34 | 272124.29 | 332407.3 | 76213.46 | 326511.23 | 141.46 | 4787.46
NCAS Financial Reports | [7 empty] | 2R17-8900 | 41765 | 2947.87 | -744.53 | 0 | -2203.34
[8 empty] | 2R17-ADM |  | 1435248.01 | 1552235.33 | 1063965.04 | 2797697.62 | 833453.9 | 1068421.24 | 130756.67 | 739402.4
[8 empty] | 2R17-7PLN |  | 209025.97 | 135163.18 | 211341 | 137086.68 | 1837.5 | 7458.08 |  | 2809.67
[8 empty] | TOTAL Planning & Admin | 41765 | 1647221.85 | 1686653.98 | 1275306.04 | 2932580.96 | 835291.4 | 1075879.32 | 130756.67 | 742212.07
Total Expenditures | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Expenditures | 0 | 0 | 0 | 855968.9 | 2559846.76 | 4891580.39 | 8883175.13 | 15144005.13 | 24575261.17 | 37337324.17 | 53082738.17 | 70032788.17 | 89126707.77 | 99519559.3058 | 109604002.8417 | 120046854.3775 | 130489705.9133 | 141182557.4492 | 151875408.985 | 159159477.985 | 166693546.985 | 174227615.985 | 181761684.985 | 189295753.985 | 196329824.985 | 203363895.985 | 210417966.985 | 217472037.985 | 224416123.985 | 230870194.985 | 233870194.985 | 235165112.985 | 236422222.985
Quarterly Projection | 0 | 0 | 0 | 855968.9 | 1703877.86 | 2331733.63 | 3991594.74 | 6260830 | 9431256.04 | 12762063 | 15745414 | 16950050 | 19093919.6 | 10392851.5358 | 10084443.5358 | 10442851.5358 | 10442851.5358 | 10692851.5358 | 10692851.5358 | 7284069 | 7534069 | 7534069 | 7534069 | 7534069 | 7034071 | 7034071 | 7054071 | 7054071 | 6944086 | 6454071 | 3000000 | 1294918 | 1257110
Actual Expenditure | 0 | 0 | 0 | 855968.9 | 2559846.76 | 4891580.39 | 8883175.13 | 15144005.13 | 27079627.19 | 39841690.19 | 52743413.74 | 69434301.7 | 87976085.3 | 102045470.48 | 113304980.63 | 125420001.55 | 131822526.3 | 138510840.12 | 148800802.35 | 154171389.97 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87 | 172971963.87
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 855968.9 | 1703877.86 | 2331733.63 | 3991594.74 | 6260830 | 11935622.06 | 12762063 | 12901723.55 | 16690887.96 | 18541783.6 | 14069385.18 | 11259510.15 | 12115020.92 | 6402524.75 | 6688313.82 | 10289962.23 | 5370587.62 | 18800573.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NCAS Financial Reports | [8 empty] | 2035572.08 | 1829937.42 | 12482110.24 | 12386644.56 | 16331262.34 | 19571835.89 | 14185763.82 | 14799265.83 | 9188278.11

## Performance Proj
Construction of New Housing | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 90 | 120 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 30 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Residential Rehab and Reconstruction | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Units | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 90 | 240 | 390 | 540 | 690 | 840 | 990 | 1140 | 1290 | 1440 | 1530 | 1610 | 1690 | 1755 | 1820 | 1870 | 1920 | 1970 | 2010 | 2030 | 2050 | 2050 | 2050 | 2050 | 2050
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 75 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 90 | 80 | 80 | 65 | 65 | 50 | 50 | 50 | 40 | 20 | 20 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 14 | 14 | 14 | 14 | 14 | 14 | 86 | 128 | 155 | 212 | 228 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 244
# of Housing Units (Populated from QPR Reporting) * | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 72 | 42 | 27 | 57 | 16 | 16
* NCORR is formalizing its beneficiary closeout procedure. Beneficiaries will be reported after going through the closeout process.
Public Facilities | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 10 | 10 | 10 | 10 | 10
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0 | [6 empty] | 5 |  |  |  | 5 |  |  |  | 5
Economic Development | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 232 | 348 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464 | 464
# of Jobs Created/Retained (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 116 | 116 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
# of Jobs Created/Retained (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Permanent Jobs Created ** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Permanent Jobs Retained ** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
** Jobs created/retained will reported at the end of the small business loans 3 year compliance period.
464
Public Infrastructure | 07/2017 | 10/2017 | 01/2018 | 4/2018 | 07/2018 | 10/2018 | 01/2019 | 4/2019 | 07/2019 | 10/2019 | 01/2020 | 4/2020 | 07/2020 | 10/2020 | 01/2021 | 4/2021 | 07/2021 | 10/2021 | 01/2022 | 4/2022 | 07/2022 | 10/2022 | 01/2023 | 4/2023 | 07/2023 | 10/2023 | 01/2024 | 4/2024 | 07/2024 | 10/2024 | 01/2025 | 4/2025 | 07/2025
Projected Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231 | 2231 | 2231 | 2231 | 2631 | 2631 | 2631 | 2631 | 2631
# of Linear Feet of Public Improvements (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements | 0
Dike/dam/stream-river bank repairs
# of Linear Feet of Public Improvements | 0
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements | 0
0

## Sheet1 (hidden)
| Lmi | Un |  | Actual Units
Edgecombe | 95 | 25
Robeson | 424 | 65 |  | 4
NCORR | 834 | 216 |  | 10
Buyout | 105 | 45
Small Rental | 125
PHA | 48
PHA | 10
| 1641 | 351 | 1992
MFH | 80
MFH | 48
128
SBR | 76
SBR | 202
SBR | 181
SBR | 5
464
Infrastructure | 2231
Infrastructure | 400
2631
Public Facilities | 1