## Intro
State of North Carolina Community Development Block Grant – Disaster Recovery (CDBG-DR) Program for Hurricane Florence Projections of Expenditures and Outcomes - as of Quarter Ending December 31, 2023 Grant # B-19-DV-37-0001, B-19-DV-37-0002 Background: The Federal Register notice authorizing North Carolina’s allocation of CDBG-DR funds requires the State to publish a projection of expenditures and outcomes. The following projections follow a HUD-specified template designed to distinguish investments in housing, non-housing and planning/administrative activities. This update reflects the entire grant amount. Reading the Projections: The HUD format contains two spreadsheets: one for financial projections and one for performance indicators. The projections indicate a month and year that corresponds to the beginning of the quarter. For example, 7/2018 represents the quarter from 7/1/2018-9/30/2018. The graphs represent cumulative expenditures over the life of the programs. Revisions: These projections will be revised as more data becomes available through the award process. Additionally, these projections will be revised following Quarterly Performance Reports submitted to HUD to reflect actual progress. Projections updated Q4 2021 are related to cost increases for materials and labor. Although costs have been reallocated to support these increasing costs in housing and non-housing programs, the projected output has not been adjusted until market conditions stabilize and a better projection is possible.

## Financial Proj
Housing | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Expenditures | 0 | 1813966 | 5697762 | 11847727.3333 | 17997692.6667 | 30252403 | 64845958 | 99439513 | 134033068 | 168626623 | 203220178 | 237813733 | 287019896 | 336226060 | 366986192 | 396885984 | 426646116 | 456406248 | 471243670 | 484995804 | 495961158 | 506000072 | 507899326 | 509798580
Quarterly Projection | 0 | 1813966 | 3883796 | 6149965.3333 | 6149965.3333 | 12254710.3333 | 34593555 | 34593555 | 34593555 | 34593555 | 34593555 | 34593555 | 49206163 | 49206164 | 30760132 | 29899792 | 29760132 | 29760132 | 14837422 | 13752134 | 10965354 | 10038914 | 1899254 | 1899254
Actual Expenditure | 0 |  |  | 1384231.37 | 3410549.2 | 13796212.22 | 33081730.56 | 39075931.48 | 59337640.48 | 56216939.04 | 84420288.3 | 100936743.25 | 125438988.36 | 165215608.73 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46 | 224875167.46
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 1356049.85 | 16515751.16 | 3656956.01 | 11552973.54 | 5994200.92 | 20261709 | -3120701.44 | 28203349.26 | 16516454.95 | 24502245.11 | 39776620.37 | 59659558.73
Non-Housing | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230770 | 461540 | 692310 | 923080 | 1153850 | 1384620 | 1615390 | 1846160 | 2076930 | 2307700 | 2538470 | 2769230 | 3000000
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230770 | 230760 | 230770
Actual Expenditure | 0 | 0 | 0 | 0 | 19335.82 | 5572.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188876.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09 | 622600.09
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188876.09 | 433724
Planning & Admin | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Expenditures | 0 | 0 | 1479939 | 2959878 | 4439817 | 5919756 | 7399694 | 8879632 | 10359570 | 11839508 | 13319446 | 14590675 | 15861904 | 17133133 | 18404362 | 19675591 | 20946820 | 22218049 | 23489278 | 24760507 | 26031736 | 27302965 | 28574194 | 29845420
Quarterly Projection | 0 | 0 | 1479939 | 1479939 | 1479939 | 1479939 | 1479938 | 1479938 | 1479938 | 1479938 | 1479938 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271229 | 1271226
Actual Expenditure | 0 | 37790 | 1037297.32 | 590898.64 | 1264108.6 | 1169764.43 | 4122278.85 | 5341227.85 | 7494871.85 | 9455326.6 | 12595369.76 | 14511875.06 | 18583300.39 | 20340741.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63 | 23153615.63
Actual Quarterly Expend (from QPRs) | 0 |  | 0 | 461139.44 | 1416992.77 | 779139.68 | 1465006.96 | 1218949 | 2153644 | 1960454.75 | 3140043.16 | 1916505.3 | 4071425.33 | 1757441.24 | 2812874
Total Expenditures | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Expenditures | 0 | 1813966 | 7177701 | 14807605.3333 | 22437509.6667 | 36172159 | 72245652 | 108319145 | 144392638 | 180466131 | 216539624 | 252635178 | 303343340 | 354051503 | 386313634 | 417715425 | 448977556 | 480239687 | 496579108 | 511833241 | 524300594 | 535841507 | 539242750 | 542644000
Quarterly Projection | 0 | 1813966 | 5363735 | 7629904.3333 | 7629904.3333 | 13734649.3333 | 36073493 | 36073493 | 36073493 | 36073493 | 36073493 | 36095554 | 50708162 | 50708163 | 32262131 | 31401791 | 31262131 | 31262131 | 16339421 | 15254133 | 12467353 | 11540913 | 3401243 | 3401250
Actual Expenditure | 0 | 37790 | 1037297.32 | 1975130.01 | 4693993.62 | 14971549.23 | 37226382.92 | 44439532.84 | 66854885.84 | 65694639.15 | 97038031.57 | 115470991.82 | 144044662.26 | 185767599.96 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69 | 248673756.69
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 1836525.29 | 17935781.44 | 4436095.69 | 13017980.5 | 7213149.92 | 22415353 | -1160246.69 | 31343392.42 | 18432960.25 | 28573670.44 | 41722937.7 | 62906156.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Performance Proj
Construction of New Housing | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72 | 96 | 120 | 144 | 168 | 192 | 216 | 240 | 260 | 260 | 260 | 260 | 260
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Residential Rehab and Reconstruction | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Units | 0 | 0 | 0 | 50 | 150 | 260 | 740 | 1220 | 1700 | 2180 | 2660 | 2980 | 3250 | 3510 | 3770 | 4030 | 4290 | 4390 | 4490 | 4590 | 4670 | 4715 | 4715 | 4715
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 50 | 100 | 110 | 480 | 480 | 480 | 480 | 480 | 320 | 270 | 260 | 260 | 260 | 260 | 100 | 100 | 100 | 80 | 45 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 18 | 32 | 44 | 107 | 225 | 327 | 327 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616
# of Housing Units (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 14 | 12 | 63 | 118 | 102 | 0 | 289
Public Facilities | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Public Services | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024 | 7/2024 | 10/2024 | 1/2025 | 4/2025 | 7/2025 | 10/2025 | 1/2026
Projected Down Payment Assistance Provided | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 17 | 27 | 37 | 57 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100
# of Down Payment Assistance Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 10 | 10 | 10 | 20 | 23 | 10 | 10 | 0 | 0 | 0 | 0 | 0
Actual # Down Payment Assistance Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Down Payment Assistance Payments (From QPR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DRGR Projections (hidden)
GRANT | PROGRAM | ACTIVITY | NATION OBJ | PROJECTED UNITS | BUDGET
FLO1 | Administration | FLO1999ADM1002 | N/a | N/a | 16826050
FLO2 | Administration | FLO2999ADM1002 | N/a | N/a | 10306150
FLO1 | Planning | FLO1999PLN9102 | N/a | N/a | 10095630
FLO2 | Planning | FLO2999PLN9102 | N/a | N/a | 6183690
FLO1 | Homeowner Recovery Program | FLO1999HRB1108 | LMH | 1888.3699 | 141338820
FLO2 | Homeowner Recovery Program | FLO2999HRB1108 | LMH | 1156.6484 | 86571660
FLO1 | Homeowner Recovery Program | FLO1999HRB1102 | UN | 809.3014 | 60573780
FLO2 | Homeowner Recovery Program | FLO2999HRB1102 | UN | 495.7064 | 37102140
FLO1 | Strategic Buyout Program | FLO1999BAM1403 | LMB | 94.1317 | 4706582.706
FLO2 | Strategic Buyout Program | FLO2999BAM1403 | LMB | 57.6567 | 2882836.278
FLO1 | Strategic Buyout Program | FLO1999BAM1404 | LMHI | 93.9813 | 9413165.412
FLO2 | Strategic Buyout Program | FLO2999BAM1404 | LMHI | 57.5646 | 5765672.556
FLO1 | Strategic Buyout Program | FLO1999BAM1402 | UN | 80.6198 | 6051320.622
FLO2 | Strategic Buyout Program | FLO2999BAM1402 | UN | 49.3806 | 3706503.786
FLO1 | Small Rental Repair Program | FLO1999SRM1508 | LMH | 201.9126 | 14133882
FLO2 | Small Rental Repair Program | FLO2999SRM1508 | LMH | 123.6738 | 8657166
FLO1 | Small Rental Repair Program | FLO1999SRM1502 | UN | 86.534 | 6057378
FLO2 | Small Rental Repair Program | FLO2999SRM1502 | UN | 53.0031 | 3710214
FLO1 | Construction Trades Training Program | FLO1999CTT9207 | LMC | 0 | 3365210
FLO2 | Construction Trades Training Program | FLO2999CTT9207 | LMC | 0 | 2061230
FLO1 | Code Enforcement Support Program | FLO1999CES1108 | LMH | 13.0232 | 2355647
FLO2 | Code Enforcement Support Program | FLO2999CES1108 | LMH | 7.9768 | 1442861
FLO1 | Code Enforcement Support Program | FLO1999CES1102 | UN | 5.5814 | 1009563
FLO2 | Code Enforcement Support Program | FLO2999CES1102 | UN | 3.4186 | 618369

## DRGR Assumptions (hidden)
National Objective | Threshold
LMI Target | 70%
UN Target | 30%
CDBG-DR Agreements | Agreement Budgets | Percentage
B-19-DV-37-0001 | 336521000 | 0.62015
B-19-DV-37-0002 | 206123000 | 0.37985
Total | 542644000
Units - Program Assumptions | Est. Cost Per Unit | Total Budget | Units - FLOR Action Plan | LMI for FLO1 | LMI for FLO2 | UN for FLO1 | UN for FLO2
Housing | 74847 | 325586400 | 4350.0261 | 1888.3699 | 1156.6484 | 809.3014 | 495.7064
Small Rental | 70000 | 32558640 | 465.1234 | 201.9126 | 123.6738 | 86.534 | 53.0031
Buyout | 50000 | 10842027.12 | 216.8405 | 94.1317 | 57.6567 | combined below | combined below
Buyout Incentive | 100160 | 21684054.24 | 216.4942 | 93.9813 | 57.5646 | 80.6198 | 49.3806
Construction Trades Training |  | 5426440 |  | 0 | 0 | N/a | N/a
Code Enforcement Support | 180881.3333 | 5426440 | 30 | 13.0232 | 7.9768 | 5.5814 | 3.4186
Budget - Program Assumptions | Total Budget | LMI for FLO1 | LMI for FLO2 | UN for FLO1 | UN for FLO2
Housing | 325586400 | 141338820 | 86571660 | 60573780 | 37102140
Small Rental | 32558640 | 14133882 | 8657166 | 6057378 | 3710214
Buyout | 10842027.12 | 4706582.706 | 2882836.278 | 2017106.874 | 1235501.262
Buyout Incentive | 21684054.24 | 9413165.412 | 5765672.556 | 4034213.748 | 2471002.524
Construction Trades Training | 5426440 | 3365210 | 2061230 | N/a | N/a
Code Enforcement Support | 5426440 | 2355647 | 1442861 | 1009563 | 618369
Administration | 27132200 | N/a | N/a | 16826050 | 10306150
Planning | 16279320 | N/a | N/a | 10095630 | 6183690